## Calendar 99
1399/03/17 | شنبه | Day7 | Sprint 1 | WEEK 1 | Current sprint
1399/03/18 | یک شنبه | Day8
1399/03/19 | دو شنبه | Day9
1399/03/20 | سه شنبه | Day10
1399/03/21 | چهار شنبه | Day11
1399/03/22 | پنج شنبه | Day12
1399/03/23 | جمعه
1399/03/24 | شنبه | Day 1 |  | WEEK 2
1399/03/25 | یک شنبه | Day 2
1399/03/26 | دو شنبه | Day 3
1399/03/27 | سه شنبه | Day 4
1399/03/28 | چهار شنبه | Day 5
1399/03/29 | پنج شنبه | Day 6
1399/03/30 | جمعه
1399/03/31 | شنبه | Day 7 | Sprint 2 | WEEK 3
1399/04/01 | یک شنبه | Day 8
1399/04/02 | دو شنبه | Day 9
1399/04/03 | سه شنبه | Day 10
1399/04/04 | چهار شنبه | Day 11
1399/04/05 | پنج شنبه | Day 12
1399/04/06 | جمعه
1399/04/07 | شنبه | Day13 |  | WEEK 4
1399/04/08 | یک شنبه | Day14
1399/04/09 | دو شنبه | Day15
1399/04/10 | سه شنبه | Day16
1399/04/11 | چهار شنبه | Day17
1399/04/12 | پنج شنبه | Day18
1399/04/13 | جمعه
1399/04/14 | شنبه | Day 1 | Sprint 3 | WEEK 5
1399/04/15 | یک شنبه | Day 2
1399/04/16 | دو شنبه | Day 3
1399/04/17 | سه شنبه | Day 4
1399/04/18 | چهار شنبه | Day 5
1399/04/19 | پنج شنبه | Day 6
1399/04/20 | جمعه
1399/04/21 | شنبه | Day 7 |  | WEEK 6
1399/04/22 | یک شنبه | Day 8
1399/04/23 | دو شنبه | Day 9
1399/04/24 | سه شنبه | Day 10
1399/04/25 | چهار شنبه | Day 11
1399/04/26 | پنج شنبه | Day 12
1399/04/27 | جمعه
1399/04/28 | شنبه | Day13 | Sprint 4 | WEEK 7
1399/04/29 | یک شنبه | Day14
1399/04/30 | دو شنبه | Day15
1399/04/31 | سه شنبه | Day16
1399/05/01 | چهار شنبه | Day17
1399/05/02 | پنج شنبه | Day18
1399/05/03 | جمعه
1399/05/04 | شنبه | Day 1 |  | WEEK 8
1399/05/05 | یک شنبه | Day 2
1399/05/06 | دو شنبه | Day 3
1399/05/07 | سه شنبه | Day 4
1399/05/08 | چهار شنبه | Day 5
1399/05/09 | پنج شنبه | Day 6
1399/05/10 | جمعه
1399/05/11 | شنبه | Day 7 | Sprint 5 | WEEK 9
1399/05/12 | یک شنبه | Day 8
1399/05/13 | دو شنبه | Day 9
1399/05/14 | سه شنبه | Day 10
1399/05/15 | چهار شنبه | Day 11
1399/05/16 | پنج شنبه | Day 12
1399/05/17 | جمعه
1399/05/18 | شنبه | Day13 |  | WEEK 10
1399/05/19 | یک شنبه | Day14
1399/05/20 | دو شنبه | Day15
1399/05/21 | سه شنبه | Day16
1399/05/22 | چهار شنبه | Day17
1399/05/23 | پنج شنبه | Day18
1399/05/24 | جمعه
1399/05/25 | شنبه | Day 1 | Sprint 6 | WEEK 11
1399/05/26 | یک شنبه | Day 2
1399/05/27 | دو شنبه | Day 3
1399/05/28 | سه شنبه | Day 4
1399/05/29 | چهار شنبه | Day 5
1399/05/30 | پنج شنبه | Day 6
1399/05/31 | جمعه
1399/06/01 | شنبه | Day 7 |  | WEEK 12
1399/06/02 | یک شنبه | Day 8
1399/06/03 | دو شنبه | Day 9
1399/06/04 | سه شنبه | Day 10
1399/06/05 | چهار شنبه | Day 11
1399/06/06 | پنج شنبه | Day 12
1399/06/07 | جمعه
1399/06/08 | شنبه | Day13 | Sprint 7 | WEEK 13
1399/06/09 | یک شنبه | Day14
1399/06/10 | دو شنبه | Day15
1399/06/11 | سه شنبه | Day16
1399/06/12 | چهار شنبه | Day17
1399/06/13 | پنج شنبه | Day18
1399/06/14 | جمعه
1399/06/15 | شنبه | Day 1 |  | WEEK 14
1399/06/16 | یک شنبه | Day 2
1399/06/17 | دو شنبه | Day 3
1399/06/18 | سه شنبه | Day 4
1399/06/19 | چهار شنبه | Day 5
1399/06/20 | پنج شنبه | Day 6
1399/06/21 | جمعه
1399/06/22 | شنبه | Day 7 | Sprint 8 | WEEK 15
1399/06/23 | یک شنبه | Day 8
1399/06/24 | دو شنبه | Day 9
1399/06/25 | سه شنبه | Day 10
1399/06/26 | چهار شنبه | Day 11
1399/06/27 | پنج شنبه | Day 12
1399/06/28 | جمعه
1399/06/29 | شنبه | Day13 |  | WEEK 16
1399/06/30 | یک شنبه | Day14
1399/06/31 | دو شنبه | Day15
1399/07/01 | سه شنبه | Day16
1399/07/02 | چهار شنبه | Day17
1399/07/03 | پنج شنبه | Day18
1399/07/04 | جمعه
1399/07/05 | شنبه | Day 1 | Sprint 9 | WEEK 17
1399/07/06 | یک شنبه | Day 2
1399/07/07 | دو شنبه | Day 3
1399/07/08 | سه شنبه | Day 4
1399/07/09 | چهار شنبه | Day 5
1399/07/10 | پنج شنبه | Day 6
1399/07/11 | جمعه
1399/07/12 | شنبه | Day 7 |  | WEEK 18
1399/07/13 | یک شنبه | Day 8
1399/07/14 | دو شنبه | Day 9
1399/07/15 | سه شنبه | Day 10
1399/07/16 | چهار شنبه | Day 11
1399/07/17 | پنج شنبه | Day 12
1399/07/18 | جمعه
1399/07/19 | شنبه | Day13 | Sprint 10 | WEEK 19
1399/07/20 | یک شنبه | Day14
1399/07/21 | دو شنبه | Day15
1399/07/22 | سه شنبه | Day16
1399/07/23 | چهار شنبه | Day17
1399/07/24 | پنج شنبه | Day18
1399/07/25 | جمعه
1399/07/26 | شنبه | Day 1 |  | WEEK 20
1399/07/27 | یک شنبه | Day 2
1399/07/28 | دو شنبه | Day 3
1399/07/29 | سه شنبه | Day 4
1399/07/30 | چهار شنبه | Day 5
1399/08/01 | پنج شنبه | Day 6
1399/08/02 | جمعه
1399/08/03 | شنبه | Day 7 | Sprint 11 | WEEK 21
1399/08/04 | یک شنبه | Day 8
1399/08/05 | دو شنبه | Day 9
1399/08/06 | سه شنبه | Day 10
1399/08/07 | چهار شنبه | Day 11
1399/08/08 | پنج شنبه | Day 12
1399/08/09 | جمعه
1399/08/10 | شنبه | Day13 |  | WEEK 22
1399/08/11 | یک شنبه | Day14
1399/08/12 | دو شنبه | Day15
1399/08/13 | سه شنبه | Day16
1399/08/14 | چهار شنبه | Day17
1399/08/15 | پنج شنبه | Day18
1399/08/16 | جمعه
1399/08/17 | شنبه | Day 1 | Sprint 12 | WEEK 23
1399/08/18 | یک شنبه | Day 2
1399/08/19 | دو شنبه | Day 3
1399/08/20 | سه شنبه | Day 4
1399/08/21 | چهار شنبه | Day 5
1399/08/22 | پنج شنبه | Day 6
1399/08/23 | جمعه
1399/08/24 | شنبه | Day 7 |  | WEEK 24
1399/08/25 | یک شنبه | Day 8
1399/08/26 | دو شنبه | Day 9
1399/08/27 | سه شنبه | Day 10
1399/08/28 | چهار شنبه | Day 11
1399/08/29 | پنج شنبه | Day 12
1399/08/30 | جمعه
1399/09/01 | شنبه | Day13 | Sprint 13 | WEEK 25
1399/09/02 | یک شنبه | Day14
1399/09/03 | دو شنبه | Day15
1399/09/04 | سه شنبه | Day16
1399/09/05 | چهار شنبه | Day17
1399/09/06 | پنج شنبه | Day18
1399/09/07 | جمعه
1399/09/08 | شنبه | Day 1 |  | WEEK 26
1399/09/09 | یک شنبه | Day 2
1399/09/10 | دو شنبه | Day 3
1399/09/11 | سه شنبه | Day 4
1399/09/12 | چهار شنبه | Day 5
1399/09/13 | پنج شنبه | Day 6
1399/09/14 | جمعه
1399/09/15 | شنبه | Day 7 | Sprint 14 | WEEK 27
1399/09/16 | یک شنبه | Day 8
1399/09/17 | دو شنبه | Day 9
1399/09/18 | سه شنبه | Day 10
1399/09/19 | چهار شنبه | Day 11
1399/09/20 | پنج شنبه | Day 12
1399/09/21 | جمعه
1399/09/22 | شنبه | Day13 |  | WEEK 28
1399/09/23 | یک شنبه | Day14
1399/09/24 | دو شنبه | Day15
1399/09/25 | سه شنبه | Day16
1399/09/26 | چهار شنبه | Day17
1399/09/27 | پنج شنبه | Day18
1399/09/28 | جمعه
1399/09/29 | شنبه | Day 1 | Sprint 15 | WEEK 29
1399/09/30 | یک شنبه | Day 2
1399/10/01 | دو شنبه | Day 3
1399/10/02 | سه شنبه | Day 4
1399/10/03 | چهار شنبه | Day 5
1399/10/04 | پنج شنبه | Day 6
1399/10/05 | جمعه
1399/10/06 | شنبه | Day 7 |  | WEEK 30
1399/10/07 | یک شنبه | Day 8
1399/10/08 | دو شنبه | Day 9
1399/10/09 | سه شنبه | Day 10
1399/10/10 | چهار شنبه | Day 11
1399/10/11 | پنج شنبه | Day 12
1399/10/12 | جمعه
1399/10/13 | شنبه | Day13 | Sprint 16 | WEEK 31
1399/10/14 | یک شنبه | Day14
1399/10/15 | دو شنبه | Day15
1399/10/16 | سه شنبه | Day16
1399/10/17 | چهار شنبه | Day17
1399/10/18 | پنج شنبه | Day18
1399/10/19 | جمعه
1399/10/20 | شنبه | Day 1 |  | WEEK 32
1399/10/21 | یک شنبه | Day 2
1399/10/22 | دو شنبه | Day 3
1399/10/23 | سه شنبه | Day 4
1399/10/24 | چهار شنبه | Day 5
1399/10/25 | پنج شنبه | Day 6
1399/10/26 | جمعه
1399/10/27 | شنبه | Day 7 | Sprint 17 | WEEK 33
1399/10/28 | یک شنبه | Day 8
1399/10/29 | دو شنبه | Day 9
1399/10/30 | سه شنبه | Day 10
1399/11/01 | چهار شنبه | Day 11
1399/11/02 | پنج شنبه | Day 12
1399/11/03 | جمعه
1399/11/04 | شنبه | Day13 |  | WEEK 34
1399/11/05 | یک شنبه | Day14
1399/11/06 | دو شنبه | Day15
1399/11/07 | سه شنبه | Day16
1399/11/08 | چهار شنبه | Day17
1399/11/09 | پنج شنبه | Day18
1399/11/10 | جمعه
1399/11/11 | شنبه | Day 1 | Sprint 18 | WEEK 35
1399/11/12 | یک شنبه | Day 2
1399/11/13 | دو شنبه | Day 3
1399/11/14 | سه شنبه | Day 4
1399/11/15 | چهار شنبه | Day 5
1399/11/16 | پنج شنبه | Day 6
1399/11/17 | جمعه
1399/11/18 | شنبه | Day 7 |  | WEEK 36
1399/11/19 | یک شنبه | Day 8
1399/11/20 | دو شنبه | Day 9
1399/11/21 | سه شنبه | Day 10
1399/11/22 | چهار شنبه | Day 11
1399/11/23 | پنج شنبه | Day 12
1399/11/24 | جمعه
1399/11/25 | شنبه | Day13 | Sprint 19 | WEEK 37
1399/11/26 | یک شنبه | Day14
1399/11/27 | دو شنبه | Day15
1399/11/28 | سه شنبه | Day16
1399/11/29 | چهار شنبه | Day17
1399/11/30 | پنج شنبه | Day18
1399/12/01 | جمعه
1399/12/02 | شنبه | Day 1 |  | WEEK 38
1399/12/03 | یک شنبه | Day 2
1399/12/04 | دو شنبه | Day 3
1399/12/05 | سه شنبه | Day 4
1399/12/06 | چهار شنبه | Day 5
1399/12/07 | پنج شنبه | Day 6
1399/12/08 | جمعه
1399/12/09 | شنبه | Day 7 | Sprint 20 | WEEK 39
1399/12/10 | یک شنبه | Day 8
1399/12/11 | دو شنبه | Day 9
1399/12/12 | سه شنبه | Day 10
1399/12/13 | چهار شنبه | Day 11
1399/12/14 | پنج شنبه | Day 12
1399/12/15 | جمعه
1399/12/16 | شنبه | Day13 |  | WEEK 40
1399/12/17 | یک شنبه | Day14
1399/12/18 | دو شنبه | Day15
1399/12/19 | سه شنبه | Day16
1399/12/20 | چهار شنبه | Day17
1399/12/21 | پنج شنبه | Day18
1399/12/22 | جمعه
1399/12/23 | شنبه |  |  | WEEK 41
1399/12/24 | یک شنبه
1399/12/25 | دو شنبه
1399/12/26 | سه شنبه
1399/12/27 | چهار شنبه
1399/12/28 | پنج شنبه
1399/12/29 | جمعه
1399/12/30 | شنبه

## Planning Tracker
| Sohrevardi | Abdolmaleki | Nosrat | Najafi | Khamseh
Capacity | 53:42 | 60:27 | 60:54 | 53:42 | 53:42
Commited Capacity | 64:40 | 41:02 | 0:00 | 43:20 | 44:30
Available Capacity | -0.45694 | 19:25 | 60:54 | 10:22 | 9:12
Task Break Down
Story ID | Sohrevardi | Abdolmaleki | Nosrat | Najafi | Khamseh
ATA-20 | 16:00 |  |  |  |  | 16
ATA-25 |  | 16:00 |  |  |  | 16
ATA-16 |  | 24:00 |  |  |  | 24
ATA-21 |  |  |  | 1:10 |  | 8
ATA-19 | 32:40 |  |  |  |  | 21
ATA-18 |  | 1:02 |  |  |  | 20 | Sohrevardi | 120.4% | In Progress
ATA-14 |  |  |  | 10:10 |  | 8 | Abdolmaleki | 67.88% | In Progress
ATA-22 | 16:00 |  |  |  |  | 16 | Nosrat | 0% | In Progress
ATA-26 |  |  |  | 24:00 |  | 24 | Najafi | 80.7% | In Progress
ATA-24 |  |  |  | 8:00 |  | 8 | Khamseh | 82.87% | In Progress
ATA-12 |  |  |  |  | 16:00 | 16
ATA-11 | [5 empty] | 8
ATA-13 |  |  |  |  | 9:00 | 8
ATA-30 |  |  |  |  | 19:30 | 24

## Capacity Calculation
calculating focus factor & final capacity |  |  | WEEK 1 | [5 empty] | WEEK 2
| Hours/Day | % Allocation | 3/17 | 3/18 | 3/19 | 3/20 | 3/21 | 3/22 | 3/24 | 3/25 | 3/26 | 3/27 | 3/28 | 3/29 | Sprint | Ceremony Time | Available Capacity | Focus Factor | Final Capacity
Sohrevardi | 8:00 | 100% | 0:00 | 8:00 | 8:00 | 8:00 | 8:00 | 4:00 | 8:00 | 8:00 | 8:00 | 8:00 | 0:00 | 4:00 | 72:00 | 12:20 | 59:40 | 90% | 53:42
Abdolmaleki | 8:50 | 100% | 8:50 | 8:50 | 8:50 | 8:50 | 8:50 | 0:00 | 8:50 | 8:50 | 8:50 | 8:50 | 0:00 | 0:00 | 79:30 | 12:20 | 67:10 | 90% | 60:27
Nosrat | 8:00 | 100% | 8:00 | 8:00 | 8:00 | 8:00 | 8:00 | 4:00 | 8:00 | 8:00 | 8:00 | 8:00 | 0:00 | 4:00 | 80:00 | 12:20 | 67:40 | 90% | 60:54
Najafi | 8:00 | 100% | 0:00 | 8:00 | 8:00 | 8:00 | 8:00 | 4:00 | 8:00 | 8:00 | 8:00 | 8:00 | 0:00 | 4:00 | 72:00 | 12:20 | 59:40 | 90% | 53:42
Khamseh | 8:00 | 100% | 0:00 | 8:00 | 8:00 | 8:00 | 8:00 | 4:00 | 8:00 | 8:00 | 8:00 | 8:00 | 0:00 | 4:00 | 72:00 | 12:20 | 59:40 | 90% | 53:42
Total |  |  | 16:50 | 40:50 | 40:50 | 40:50 | 40:50 | 16:00 | 40:50 | 40:50 | 40:50 | 40:50 | 0:00 | 16:00 | 375:30 | 61:40 | 313:50 |  | 282:27

## Ceremony Time
Ceremony Time | Minute / Day /Ceremony
| WEEK 1 | [5 empty] | WEEK 2
ceremonies | 3/17 | 3/18 | 3/19 | 3/20 | 3/21 | 3/22 | 3/24 | 3/25 | 3/26 | 3/27 | 3/28 | 3/29 | Total Min
Daily Scrum Call | 0:20 | 0:20 | 0:20 | 0:20 | 0:20 | 0:20 | 0:20 | 0:20 | 0:20 | 0:20 | 0:00 | 0:00 | 3:20
Grooming | 1:00 | 0:00 | 0:00 | 1:00 | 0:00 | 0:00 | 1:00 | 0:00 | 0:00 | 1:00 | 0:00 | 0:00 | 4:00
Sprint Planning -Day 1 | 2:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 2:00
Sprint review /Demo | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 2:00 | 2:00
Retrospective | WEEK 2 3/29: 1:00 | 1:00
Total | [12 empty] | 12:20

## Sprint Calendar
Sprint 1 Calendar
Week1 |  | شنبه | یک شنبه | دو شنبه | سه شنبه | چهارشنبه | پنج شنبه
|  | 1399/03/17 | 1399/03/18 | 1399/03/19 | 1399/03/20 | 1399/03/21 | 1399/03/22
| Sprint 1 | Day1 | Day2 | Day3 | Day4 | Day5 | Day6
Week2 |  | شنبه | یک شنبه | دو شنبه | سه شنبه | چهارشنبه | پنج شنبه
|  | 1399/03/24 | 1399/03/25 | 1399/03/26 | 1399/03/27 | 1399/03/28 | 1399/03/29
|  | Day7 | Day8 | Day9 | Day10 | Day11 | Day12
| legends | Day7: Previous Sprint
Current Sprint

## Team
Team Member | Role | % Allocation | Hours/Day | Hours/Sprint
Sohrevardi | Developer | 100% | 8 | 80
Abdolmaleki | Developer | 100% | 8 | 80
Nosrat | Developer | 100% | 8 | 80
Najafi | Developer | 100% | 8 | 80
Khamseh | Developer | 100% | 8 | 80
|  |  | 40 | 400

## Sprint Calendar(2)
Sprint 2 Calendar
Week1 |  | شنبه | یک شنبه | دو شنبه | سه شنبه | چهارشنبه | پنج شنبه
| 1399/03/29 | 1399/03/31 | 1399/04/01 | 1399/04/02 | 1399/04/03 | 1399/04/04 | 1399/04/05
| Sprint 1 |  | Day1 | Day2 | Day3 | Day4 | Day5
Week2 |  | شنبه | یک شنبه | دو شنبه | سه شنبه | چهارشنبه | پنج شنبه
|  | 1399/04/07 | 1399/04/08 | 1399/04/09 | 1399/04/10 | 1399/04/11 | 1399/04/12
|  | Day6 | Day7 | Day8 | Day9 | Day10 | Day11
| legends | Day6: Previous Sprint
Current Sprint

## Sprint(2) Team
Team Member | Role | % Allocation | Hours/Day | Hours/Sprint
Sohrevardi | Developer | 80% | 8 | 70
Abdolmaleki | Developer | 80% | 8 | 70
Nosrat | Developer | 100% | 8 | 88
Najafi | Developer | 100% | 8 | 88
Khamseh | Developer | 100% | 8 | 88
|  |  | 40 | 404

## Sprint(2) Ceremony Time
Ceremony Time | Minute / Day /Ceremony
| WEEK 1 |  |  |  |  | WEEK 2
ceremonies | 04/01 | 04/02 | 04/03 | 04/04 | 04/05 | 04/07 | 04/08 | 04/09 | 04/10 | 04/11 | 04/12 | Total Min
Daily Scrum Call | 0:20 | 0:20 | 0:20 | 0:20 | 0:20 | 0:00 | 0:20 | 0:20 | 0:20 | 0:20 | 0:00 | 3:00
Grooming | 1:00 | 0:00 | 0:00 | 1:00 | 0:00 | 0:00 | 1:00 | 0:00 | 0:00 | 0.00.00 | 1:00 | 4:00
Sprint Planning -Day 1 | 2:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 2:00
Sprint review /Demo | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 2:00 | 2:00
Retrospective | WEEK 2 04/12: 1:00 | 1:00
Total | [11 empty] | 12:00

## Sprint(2) Capacity calculation
calculating focus factor & final capacity |  |  | WEEK 1 | [5 empty] | WEEK 2
| Hours/Day | % Allocation | 4/01 | 4/02 | 4/03 | 4/04 | 4/05 | 4/07 | 4/08 | 4/09 | 4/10 | 4/11 | 4/12 | Sprint | Ceremony Time | Available Capacity | Focus Factor | Final Capacity
Sohrevardi | 8:00 | 80% | 8:00 | 8:00 | 8:00 | 8:00 | 4:00 | 8:00 | 8:00 | 8:00 | 8:00 | 8:00 | 4:00 | 64:00 | 12:00 | 52:00 | 90% | 46:48
Abdolmaleki | 8:50 | 80% | 8:50 | 8:50 | 8:50 | 8:50 | 0:00 | 8:50 | 8:50 | 8:50 | 8:50 | 8:50 | 0:00 | 63:36 | 12:00 | 51:36 | 90% | 46:26
Nosrat | 8:00 | 100% | 8:00 | 8:00 | 8:00 | 8:00 | 4:00 | 8:00 | 8:00 | 8:00 | 8:00 | 8:00 | 4:00 | 80:00 | 12:00 | 68:00 | 90% | 61:12
Najafi | 8:00 | 100% | 8:00 | 8:00 | 8:00 | 8:00 | 4:00 | 8:00 | 8:00 | 8:00 | 8:00 | 8:00 | 4:00 | 80:00 | 12:00 | 68:00 | 90% | 61:12
Khamseh | 8:00 | 100% | 8:00 | 8:00 | 8:00 | 8:00 | 4:00 | 8:00 | 8:00 | 8:00 | 8:00 | 8:00 | 4:00 | 80:00 | 12:00 | 68:00 | 90% | 61:12
Total |  |  | 40:50 | 40:50 | 40:50 | 40:50 | 16:00 | 40:50 | 40:50 | 40:50 | 40:50 | 40:50 | 16:00 | 399:30 | 60:00 | 307:36 |  | 276:50

## Sprint(2) Planning Tracker
| Sohrevardi | Abdolmaleki | Nosrat | Najafi | Khamseh
Capacity | 46:48 | 46:26 | 61:12 | 61:12 | 61:12
Commited Capacity | 40:00 | 37:00 | 24:00 | 40:00 | 46:00
Available Capacity | 6:48 | 9:26 | 37:12 | 21:12 | 15:12
Task Break Down
Story ID | Sohrevardi | Abdolmaleki | Nosrat | Najafi | Khamseh
ATA-54 Front comment & like & dislike |  |  |  |  | 4:00
ATA-52 Backend series | 32:00 |  |  |  |  | 21:20
ATA-51 Front VOD categories |  |  |  |  | 2:00
ATA-50 Backend VOD categories |  | 16:00 |  |  |  | 4:00
ATA-49 Backend calculate discount |  | 5:00 |  |  |  | 5:00
ATA-48 Front VOD Metadata |  |  |  |  | 8:00 | 7:00 | Sohrevardi | 85.47% | In Progress
ATA-47 Backend VOD Metadata |  |  |  | 16:00 |  | 8:00 | Abdolmaleki | 79.67% | In Progress
ATA-46 Backend Captcha |  | 16:00 |  |  |  | 18:00 | Nosrat | 39.22% | In Progress
ATA-43 backend vod comment |  |  |  | 24:00 |  | 33:20 | Najafi | 65.36% | In Progress
ATA-41 Back office R&D |  |  | 24:00 |  |  |  | Khamseh | 75.16% | In Progress
ATA-39 VideoJS VTT Support |  |  |  |  | 8:00 | 6:00
ATA-37 videojs multi Audio Tracks |  |  |  |  | 2:00 | 4:00
ATA-36 subtitle suport with videojs |  |  |  |  | 4:00 | 1:00
ATA-35 replace videojs with old video player |  |  |  |  | 8:00 | 11:40
ATA-32 Front IPG factor |  |  |  |  | 6:00 | 28:35
ATA-23 backend child lock(PGAA) | 8:00 |  |  |  |  | 14:00
ATA-15 thumbnail |  |  |  |  | 4:00 | 3:00
ATA-10 AES128 TS |  |  |  |  | 2:00 | 4:00
ATA-9 Quality management |  |  |  |  | 4:00 | 4:15
ATA-4 responsive-menu-footer |  |  |  |  | 8:00
ATA-3 Front user profile with PGAA |  |  |  |  | 8:00
Note on F17: Shahab Moghadam: